Perfect — let’s expand your Innovation Hub launch plan into a detailed Gantt-style timeline with tasks, owners, and deadlines. Since we’re targeting January 2026, I’ll map activities across Nov 2025 – Mar 2026.

📊 Gantt-Style Timeline: Innovation Hub Launch

| Phase / Task | Owner | Start Date | End Date | Notes |
| --- | --- | --- | --- | --- |
| Preparation (Nov–Dec 2025) |  |  |  |  |
| Define objectives & success metrics | Innovation Lead | Nov 3, 2025 | Nov 10, 2025 | Align with leadership vision |
| Draft governance policies | Policy Team + Legal | Nov 10, 2025 | Nov 24, 2025 | Cover submissions, IP, confidentiality |
| Stakeholder alignment workshops | Project Manager | Nov 17, 2025 | Nov 28, 2025 | Secure buy-in from HR, IT, Comms |
| Build (Dec 2025) |  |  |  |  |
| Design intranet hub page | IT + Comms | Dec 1, 2025 | Dec 10, 2025 | Branding, navigation, FAQs |
| Develop idea submission form | IT | Dec 5, 2025 | Dec 12, 2025 | Fields: title, description, impact |
| Develop insight submission form | IT | Dec 5, 2025 | Dec 12, 2025 | Fields: source, relevance |
| Build ideas list repository | IT | Dec 10, 2025 | Dec 17, 2025 | Searchable, status tracking |
| Build insights list repository | IT | Dec 10, 2025 | Dec 17, 2025 | Categorized, tagged |
| Internal testing & QA | Project Manager + IT | Dec 18, 2025 | Dec 22, 2025 | Ensure usability |
| Communications (Dec 2025–Jan 2026) |  |  |  |  |
| Pre-launch teaser campaign | Comms Team | Dec 8, 2025 | Dec 22, 2025 | Posters, intranet banners |
| Draft launch announcement | Comms + CEO Office | Dec 15, 2025 | Dec 22, 2025 | Video + email |
| Training sessions (recorded + live) | HR + Comms | Jan 5, 2026 | Jan 15, 2026 | Short webinars |
| Launch (Jan 2026) |  |  |  |  |
| Go-live event (town hall) | CEO + Comms | Jan 12, 2026 | Jan 12, 2026 | Demo hub features |
| Open submissions | All staff | Jan 12, 2026 | Jan 31, 2026 | Encourage first wave |
| Monitor engagement metrics | Project Manager | Jan 12, 2026 | Jan 31, 2026 | Track submissions, active users |
| Post-Launch (Feb–Mar 2026) |  |  |  |  |
| Collect feedback & refine forms | Project Manager + IT | Feb 1, 2026 | Feb 15, 2026 | Adjust based on user input |
| Recognition program setup | HR + Comms | Feb 10, 2026 | Feb 20, 2026 | Quarterly awards |
| Continuous improvement updates | IT + Comms | Feb 15, 2026 | Mar 15, 2026 | Add voting, commenting features |

🔑 Key Highlights

- Preparation ensures governance and stakeholder buy-in before building.

- Build focuses on technical delivery of forms, lists, and intranet hub.

- Communications drives awareness and adoption through teasers, announcements, and training.

- Launch is anchored by a town hall event and open submissions.

- Post-Launch emphasizes feedback loops, recognition, and continuous improvement.

Would you like me to visualize this timeline as a Gantt chart graphic so you can see dependencies and overlaps more clearly?

🚀 Project Plan: Innovation Hub Launch (January 2026)

1. Preparation Phase (Nov–Dec 2025)

- Define objectives: Clarify the purpose of the hub (e.g., fostering creativity, capturing insights, driving innovation projects).

- Policy development: Draft governance policies covering:

  - Submission guidelines for ideas/insights

  - Review and approval processes

  - Intellectual property and confidentiality rules

  - Recognition and rewards framework

- Stakeholder alignment: Engage leadership, HR, IT, and communications teams to secure buy-in and resources.

2. Build Phase (Dec 2025)

- Intranet page:

  - Central hub with overview, mission, and navigation to forms/lists

  - FAQs and policy documents

  - Contact details for support

- Idea form:

  - Simple submission form (title, description, potential impact, department)

  - Option to attach files or links

- Insight form:

  - Capture observations, market trends, customer feedback

  - Fields for source, relevance, and suggested action

- Ideas list:

  - Dynamic, searchable repository of submitted ideas

  - Status tracking (new, under review, approved, implemented)

- Insights list:

  - Categorized repository of insights (market, customer, internal process)

  - Tags for easy filtering

3. Communications Plan (Dec 2025–Jan 2026)

- Pre-launch teaser campaign:

  - Email newsletters, posters, intranet banners

  - “Innovation Hub is coming January 2026!”

- Launch announcement:

  - CEO/leadership message

  - Video introduction explaining purpose and how to participate

- Training sessions:

  - Short webinars or workshops on using the hub

- Ongoing engagement:

  - Monthly spotlight on top ideas/insights

  - Recognition of contributors

  - Success stories shared across the organization

4. Launch Phase (January 2026)

- Go-live event:

  - Kickoff meeting or town hall

  - Live demo of the hub

- Open submissions:

  - Encourage first wave of ideas and insights

- Monitor engagement:

  - Track usage metrics (number of submissions, active users)

  - Collect feedback for improvements

5. Post-Launch (Feb–Mar 2026)

- Review and refine:

  - Adjust forms, lists, and policies based on feedback

- Recognition program:

  - Quarterly awards for best ideas/insights

- Continuous improvement:

  - Regular updates to intranet page

  - New features (e.g., voting, commenting, analytics dashboard)

📊 Timeline Overview

| Phase | Timeline | Key Deliverables |
| --- | --- | --- |
| Preparation | Nov–Dec 2025 | Objectives, policies, stakeholder buy-in |
| Build | Dec 2025 | Intranet page, forms, lists |
| Communications | Dec 2025–Jan 2026 | Teasers, launch announcement, training |
| Launch | Jan 2026 | Go-live event, open submissions |
| Post-Launch | Feb–Mar 2026 | Feedback loop, recognition, improvements |

Would you like me to expand this into a detailed Gantt-style timeline with tasks, owners, and deadlines, or keep it at this strategic level?