Here’s a summary of the key action items (i.e., things agencies must or should do) under the Australian Government’s “Policy for the Responsible Use of AI in Government” (digital.gov.au).

Summary of Action Items from the AI Policy

1. Assign Accountable Official(s) (“Enable & Prepare”)

- Agencies must designate one or more “accountable officials” responsible for implementing the AI policy. (digital.gov.au)

- This must be done within 90 days of the policy taking effect (i.e., by 30 November 2024). (digital.gov.au)

- The accountable official(s) must: (digital.gov.au)

  - Lead policy implementation in their agency. (digital.gov.au)

  - Notify the Digital Transformation Agency (DTA) when a new high-risk AI use case is identified. (digital.gov.au)

  - Serve as a point of contact for whole-of-government AI coordination. (digital.gov.au)

  - Participate (or delegate) in cross-government AI forums and processes. (digital.gov.au)

  - Keep up to date with evolving policy requirements. (digital.gov.au)

- When appointing or changing accountable official(s), agencies must email the DTA (ai@dta.gov.au) with contact details. (digital.gov.au)

- It’s strongly recommended (but not mandatory) that agencies run AI fundamentals training for all staff within 6 months, plus extra role-specific training for those deeply involved in AI. (digital.gov.au)

- Agencies should map their existing/internal use of AI, e.g., by creating a register of where they already use AI. (digital.gov.au)

- Integrate AI considerations into other existing agency frameworks (privacy, security, data, records, etc.). (digital.gov.au)

2. Publish a Public Transparency Statement (“Engage Responsibly”)

- Agencies must publish a Transparency Statement about their AI use within 6 months of the policy’s start — by 28 February 2025. (digital.gov.au)

- This statement must: (digital.gov.au)

  - Describe how the agency is using (or planning to use) AI; why it’s using it. (digital.gov.au)

  - Classify the uses of AI by “usage patterns” and “domains.” (digital.gov.au)

  - Indicate where the public might directly interact with AI or be significantly affected. (digital.gov.au)

  - Explain how the agency monitors the effectiveness of its AI systems (e.g., governance, checking performance). (digital.gov.au)

  - Describe how the agency protects against potential negative impacts on the public. (digital.gov.au)

  - State how the agency complies with legal/regulatory obligations. (digital.gov.au)

  - Provide the date of the most recent update to the statement. (digital.gov.au)

- The statement must be written in clear, plain language (avoid jargon) and include or link to a public contact email. (digital.gov.au)

- The statement must be reviewed and updated: at least once a year, or sooner if there are significant changes (e.g., major shift in how AI is used). (digital.gov.au)

- When the statement is published or updated, the accountable official should send a link to the DTA (via ai@dta.gov.au). (digital.gov.au)

3. Implement Technical Standards (“Evolve & Integrate”)

- Agencies should follow the AI Technical Standard that covers the full AI system lifecycle: from design, development, deployment, to decommissioning. (digital.gov.au)

- Key technical practices (from the standard) include: (digital.gov.au)

  - Operational model: define how the AI system will operate securely. (digital.gov.au)

  - Reference architecture: either use or evaluate existing architecture patterns. (digital.gov.au)

  - Team capability: assign roles (business, tech) and build AI skills via regular training. (digital.gov.au)

  - Auditability: build mechanisms to audit data and models over time. (digital.gov.au)

  - Explainability: make sure the system’s decisions, limitations, and data use can be explained to users. (digital.gov.au)

  - Bias management: identify, assess, and mitigate bias that could affect people, data, or processes. (digital.gov.au)

  - Version control: put versioning practices in place for model/data/model changes. (digital.gov.au)

  - There are also detailed life-cycle statements for design, data, training, evaluation, deployment, monitoring, testing safety & robustness, and decommissioning. (digital.gov.au)

  - For example, Statement 28 requires rigorous testing for safety, reliability, performance, stress, adversarial risk, etc. (digital.gov.au)

- Agencies should monitor and evaluate their AI governance, internal policy, and risk as AI systems evolve. (digital.gov.au)

- They should embed feedback mechanisms so the policy and practice can adapt over time as technology changes. (digital.gov.au)

- They should participate in whole-of-government capacity building, to build consistent AI maturity across agencies. (digital.gov.au)

Optional / Recommended Actions

- Agencies are encouraged to take part in the government’s AI assurance framework pilot. (digital.gov.au)

- Apply the DTA’s guidance for using public generative AI tools in appropriate contexts. (digital.gov.au)

- Regularly review internal AI governance to ensure it remains fit for purpose. (digital.gov.au)

- Maintain engagement with the broader digital community (forums, training, peer agencies) to stay current.

Here is a clean, practical checklist based on the Australian Government Policy for the Responsible Use of AI in Government (v1.1).

AI Policy Compliance Checklist (Agency-Level)

✅ 1. Appoint Accountable Official(s)

- Appoint one or more Accountable Officials (AOs)

- Complete appointment by 30 November 2024

- Email AO details to ai@dta.gov.au

- Put process in place to notify DTA whenever:

  - A new high-risk AI use case is identified

  - An existing AI use case becomes high-risk

- Ensure AO participates in cross-government AI forums

- Ensure AO stays current on AI policy changes

Recommended (not mandatory)

- Provide “AI fundamentals” training for all staff

- Provide role-specific training for relevant staff

- Create/maintain internal AI use register

- Integrate AI governance into existing frameworks (risk, data, privacy, cyber security, ethics, etc.)

✅ 2. Publish a Public AI Transparency Statement

Must be completed by 28 February 2025

- Publish a clear, plain-language transparency statement covering:

  - Intent behind AI use (why the agency uses AI)

  - Classification of AI use by pattern & domain

  - Identification of public-facing or high-impact AI use

  - Governance and performance monitoring approach

  - Measures to prevent negative public impact

  - Explanation of legal and regulatory compliance

  - Last-updated date

  - Public contact email

- Review and update the statement:

  - At least annually

  - When significant changes occur

  - When new factors materially affect prior statements

- Send published/updated link to ai@dta.gov.au

✅ 3. Apply the AI Technical Standard (Full Lifecycle)

Governance & Capability

- Ensure proper resourcing, roles, and skills for AI work

- Maintain training plans for AI practitioners and business owners

Design & Development

- Conduct risk assessments and identify potential biases

- Ensure data quality, provenance, and suitability checks

- Maintain documentation for datasets, models, decisions

Auditability & Explainability

- Implement audit trails for data, model versions, decisions

- Ensure decisions or outputs can be reasonably explained

Testing & Safety

- Test for:

  - Accuracy

  - Reliability

  - Performance

  - Bias/fairness

  - Security & adversarial robustness

  - Stress and edge-case scenarios

Deployment & Monitoring

- Put continuous monitoring processes in place

- Detect model drift or unexpected behaviour

- Maintain version control for data, models, components

Decommissioning

- Establish approach to retire AI systems safely

- Preserve necessary records and evidence

✅ 4. Continuous Improvement & Coordination

- Regularly measure maturity and implementation progress

- AO reports issues or insights back to DTA when relevant

- Participate in whole-of-government AI capability activities

- Build AI governance into agency strategy and planning

✅ 5. Recommended Additional Actions (Optional but Valuable)

- Maintain an agency-wide AI inventory/register

- Align internal AI policy to whole-of-government AI policy

- Participate in the AI Assurance Framework pilot

- Encourage staff participation in cross-agency AI communities

Here is a structured project plan based on the checklist — organised into phases, milestones, tasks, owners, and deadlines.
(If you want, I can also generate this as a Gantt chart, PDF, PowerPoint, or MS Project–style file.)

AI Policy Implementation Project Plan

Aligned to the Australian Government Policy for the Responsible Use of AI in Government (v1.1)

Phase 1 — Project Initiation (Week 1–2)

Objectives

Establish governance structure, confirm scope, and initiate policy-compliance work.

Key Tasks

| Task | Description | Owner | Due |
| --- | --- | --- | --- |
| 1.1 Appoint Project Sponsor | Senior SES to sponsor compliance | Agency executive | Week 1 |
| 1.2 Establish AI Policy Implementation Team | Form working group (policy, legal, ICT, data, risk, comms) | Sponsor / CIO | Week 1 |
| 1.3 Define project scope & timelines | Agree on deliverables, governance, reporting | Project Manager | Week 2 |
| 1.4 Kick-off meeting | Confirm responsibilities and milestones | PM / AO(s) | Week 2 |

Phase 2 — Appoint Accountable Official(s) (Week 1–4)

Objectives

Ensure agency meets mandatory requirement to designate accountable official(s).

Key Tasks

| Task | Description | Owner | Due |
| --- | --- | --- | --- |
| 2.1 Identify candidate AO(s) | SES Band decision | Agency executive | Week 2 |
| 2.2 Formal appointment of AO(s) | Internal approval process | Executive | Week 3 |
| 2.3 Notify DTA of AO details | Email ai@dta.gov.au | AO / PMO | Week 4 |
| 2.4 Define AO responsibilities internally | Document reporting lines, scope, decision rights | PMO | Week 4 |
| 2.5 Establish AO participation in cross-government AI forums | Register AO/Delegate in DTA channels | AO | Ongoing |

Milestone: Accountable Official(s) appointed and registered with DTA.

Phase 3 — AI Use Mapping & Governance Integration (Week 3–10)

Objectives

Understand current AI landscape and ensure AI governance integrates with existing agency frameworks.

Key Tasks

| Task | Description | Owner | Due |
| --- | --- | --- | --- |
| 3.1 Conduct AI inventory audit | Identify existing and emerging AI use cases | PM / ICT / data teams | Week 6 |
| 3.2 Classify use cases by risk and domain | Align with DTA classification frameworks | PM + AO | Week 7 |
| 3.3 Identify high-risk cases for DTA notification | Assess according to policy | AO | Week 8 |
| 3.4 Integrate AI policy requirements into agency frameworks | Risk, privacy, data, cyber, HR, ICT architecture | Policy + Risk + ICT | Week 10 |
| 3.5 Develop internal AI governance playbook | Decision rights, risk gates, approval workflow | PM / Policy team | Week 10 |

Milestone: Internal AI register completed and governance integrated.

Phase 4 — Workforce Capability & Training (Week 6–16)

Objectives

Equip staff with foundational and specialist skills to support responsible AI use.

Key Tasks

| Task | Description | Owner | Due |
| --- | --- | --- | --- |
| 4.1 Determine training needs | Identify priority groups (legal, ICT, data, procurement, comms) | HR / PM | Week 8 |
| 4.2 Roll out “AI fundamentals” training | Whole-of-agency baseline training | HR | Week 12 |
| 4.3 Specialist training for technical roles | For AI developers, data scientists, model evaluators | ICT / HR | Week 16 |
| 4.4 Update induction & ongoing learning pathways | Embed sustainability of capabilities | HR | Week 16 |

Milestone: Agency-wide AI capability uplift underway.

Phase 5 — Transparency Statement Development (Week 10–22)

Deadline: 28 February 2025

Objectives

Produce required public transparency statement in line with DTA standard.

Key Tasks

| Task | Description | Owner | Due |
| --- | --- | --- | --- |
| 5.1 Draft transparency statement | Describe intent, use cases, classification, risks, safeguards | PM / Policy team | Week 16 |
| 5.2 Conduct internal legal/privacy review | Privacy, FOI, regulatory alignment | Legal | Week 18 |
| 5.3 Validate technical accuracy | Check descriptions of AI systems and monitoring | ICT / Data | Week 18 |
| 5.4 Senior executive approval | SES endorsement for publication | Sponsor | Week 20 |
| 5.5 Publish on agency website | Comms + Web team | Week 21 |  |
| 5.6 Notify DTA with link | Email ai@dta.gov.au | AO | Week 22 |

Milestone: Transparency statement published before 28 Feb 2025 deadline.

Phase 6 — Apply Technical Standard for AI Systems (Ongoing from Week 12)

Objectives

Ensure all new or existing AI systems follow the AI Technical Standard across the lifecycle.

Key Tasks

| Task | Description | Owner | Frequency |
| --- | --- | --- | --- |
| 6.1 Evaluate AI projects against the Technical Standard | Design → development → deployment | ICT / Data / Risk | Ongoing |
| 6.2 Establish version control & auditability requirements | For data, models, decisions | ICT | Ongoing |
| 6.3 Implement performance, safety & robustness testing | Bias, stress tests, adversarial risk | Data science / QA | Pre-deployment |
| 6.4 Set up continuous monitoring | Drift detection, performance logs | ICT / Ops | Post-deployment |
| 6.5 Define decommissioning processes | Archival, record-keeping, risk closure | ICT / Records | As needed |

Milestone: All AI systems compliant with Technical Standard.

Phase 7 — Reporting, Review & Continuous Improvement (Ongoing)

Objectives

Monitor compliance, evolve governance, and maintain alignment with whole-of-government guidance.

Key Tasks

| Task | Description | Owner | Frequency |
| --- | --- | --- | --- |
| 7.1 Annual review of transparency statement | Update significant changes | AO / PM | Annually |
| 7.2 Annual maturity assessment | Evaluate capability growth | AO / PM | Annually |
| 7.3 Review AI register | Log new AI systems and retirements | PM / ICT | Quarterly |
| 7.4 Participate in DTA AI forums | Agency representation | AO / Delegate | Ongoing |
| 7.5 Engage with AI Assurance Framework pilot | Where relevant | AO / ICT / Risk | As needed |

Milestone: Agency maintains continuous compliance and improvement.